## Sheet1
Project | DD | Remaining-Days | Champion | Status | Project Name: | Python 2
Data Extraction | 2025-02-28 | 0 | Omar | Completed | Lead: | Omar Althwaini
Bulk Download | 2025-02-28 | 0 | Omar | Completed | Team Members: | James, Maria, Africa, Emiiano
API Connection | 2025-02-28 | 0 | Maria | Completed | Due Date: | 2025-03-16
ETL | 2025-02-28 | 0 | Omar | Completed
Combine the data sets | 2025-02-28 | 0 | Omar | Completed
Remove Duplicates | 2025-02-28 | 0 | Omar | Completed
Work with Null values | 2025-02-28 | 0 | Omar | Completed
Select 5 companies | 2025-02-28 | 0 | Omar | Completed
Fix Data Types | 2025-02-28 | 0 | Omar | Completed
Add new data-points that will help in ML prediction | 2025-02-28 | 0 | Omar | Completed
Save the final file | 2025-02-28 | 0 | Omar | Completed
ML | 2025-03-12 | 0 | Afirca | Completed
Field Research | 2025-03-08 | 0 | James | Completed
Adding relavent feauters | 2025-03-08 | 0 | James | Completed
Visualize the data | 2025-03-09 | 0 | Africa | Completed
Visualize the correlation | 2025-03-09 | 0 | Africa | Completed
Prepare date for ML | 2025-03-09 | 0 | Africa | Completed
Develop the ML model | 2025-03-09 | 0 | Africa | Completed
Prediction with live data | 2025-03-11 | 0 | Maria | Completed
StreamLit | 2025-03-11 | 0 | Maria | Completed
Documentation & QA | 2025-03-14 | 2 | Emiliano | In-Progress
Formulas:
Remaining-Days = IF(Table1[[#This Row],[Status]]=("Completed"),0,Table1[[#This Row],[DD]]-TODAY())